## Slide 1
Azure DevOps -> GitHub Enterprise
Phase 1 Migration Plan & Effort Estimation
100 Repositories | Repos + PRs + Commits | MoJ Entra ID
Boards & Release Pipelines remain in Azure DevOps
Azure Boards GitHub App wires the two ends together
Saudi Arabia Ministry of Justice | Platform Engineering
Version 1.0
Notes: Welcome and framing. Today we are walking through the detailed Phase 1 plan to migrate 100 Azure DevOps repositories to GitHub Enterprise, keeping Boards and release pipelines in Azure DevOps. Key message: this is the lowest-risk path. We move code only, and we preserve the existing release investment.

## Slide 2
Executive Summary
What we are doing, and what we are deliberately not doing in Phase 1
IN SCOPE - PHASE 1
- 100 ADO repositories migrated to GHE (EMU)
- Full commit history, all branches, all tags
- Open + closed Pull Requests with comments
- LFS objects and attachments
- MoJ Entra ID SSO + SCIM provisioning
- Branch protection re-implemented as GHE rulesets
- Azure Pipelines re-pointed to GitHub source
- Azure Boards GitHub App for AB#123 linking
DEFERRED TO PHASE 2
- Migrate CI / Build pipelines to GitHub Actions
- Migrate Release pipelines to Actions Environments
- Self-hosted runners (Azure VMSS) at scale
- OIDC federation to Azure subscriptions
- Decommission Azure Pipelines & Releases
- Migrate work items / Boards (only if requested)
- Org consolidation (95 ADO -> N GHE orgs)
10
weeks duration
8
team members
~5.3
peak FTE
150
person-days effort
4 + Pilot
migration waves
5
L1 milestones
STRATEGIC POSITION
Phase 1 is the lowest-risk path to land 100 repos behind MoJ SSO while preserving the existing CD investment.
ADO Pipelines & Releases continue unchanged; only the source repository is re-pointed to GitHub.
Azure Boards stays as the work-management system of record; AB#123 references keep traceability intact.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
2 / 18
Notes: Frame what is in and out. In scope: 100 repos with full history, PRs, commits, LFS; MoJ Entra SSO + SCIM; rulesets replacing ADO branch policies; ADO Pipelines re-pointed at GitHub source; Azure Boards GitHub App for AB#123 linking. Deferred to Phase 2: anything that touches CI/CD or work-item migration. Headline numbers: 10 weeks, 8 people, 5.3 peak FTE, 150 person-days.

## Slide 3
Target Architecture - Phase 1
Hybrid model: code in GitHub, work items + releases in Azure
MoJ Microsoft Entra ID
GitHub Enterprise (EMU)
- 100 repositories (1:1 with ADO orgs)
- Commits, branches, tags, history
- Pull Requests + comments
- LFS + attachments
- Rulesets (replicating ADO branch policies)
- CODEOWNERS
- Optional: GitHub Advanced Security
Azure DevOps
- Work Items + Boards (unchanged)
- Build pipelines (source -> GitHub)
- Release pipelines (unchanged)
- Service connections to Azure (unchanged)
- Artifacts feeds (unchanged)
- Wikis (unchanged for now)
Azure Boards GitHub App -- AB#123 references link commits / PRs / branches both ways and auto-transition work item state on PR merge
Saudi MoJ | ADO -> GHE | Phase 1 Plan
3 / 18
Notes: The architecture is deliberately hybrid. GitHub Enterprise (EMU) becomes the source of truth for code. Azure DevOps keeps work items, boards, pipelines, releases, service connections, artifacts, and wikis. MoJ Entra ID authenticates both ends. The Azure Boards GitHub App is the wire between the two systems and is what makes the hybrid feel seamless to developers.

## Slide 4
Azure Boards <-> GitHub Linking
How AB#123 references keep work items in ADO and code in GitHub stitched together
Developer commits / opens PR in GitHub
Mentions AB#123 in commit msg, PR title, or branch name
Azure Boards GitHub App detects reference
ADO work item links to the GitHub PR / commit / branch
On PR merge, ADO work item auto-transitions state
Capabilities provided by the integration
Capability | Works? | Notes
Link GitHub PR <-> ADO work item | Yes | Two-way visibility on both platforms
Link GitHub commit <-> ADO work item | Yes | Reference in commit message
Link GitHub branch <-> ADO work item | Yes | Reference in branch name
Auto-state-transition on PR merge | Yes | Configurable via ADO process template
Multiple ADO projects -> one GHE org | Yes | Multi-project mapping supported
Multiple GHE orgs -> one ADO org | Yes | Install per ADO org
Saudi MoJ | ADO -> GHE | Phase 1 Plan
4 / 18
Notes: The integration is what removes the main objection to splitting code from work items. Developers type AB#123 in a commit, branch, or PR. The Boards App sees it, and both sides show the link. On PR merge, the linked work item auto-transitions state. We verify all five capabilities listed during the pilot wave before scaling.

## Slide 5
Pre-requisites
Must be in place before Week 1 kick-off
# | Category | Pre-requisite
1 | Commercial | GHE Enterprise (EMU) contract signed and tenant provisioned
2 | Commercial | GHE seat count confirmed >= 500 active users
3 | Commercial | Decision: GitHub Advanced Security in or out of Phase 1
4 | Identity | MoJ Entra ID tenant admin available for SAML + SCIM in Weeks 3-4
5 | Identity | Identity mapping spreadsheet started (ADO user -> Entra UPN -> EMU)
6 | Identity | Service principal in Entra for SCIM provisioning to GHE
7 | Source-side | Project Collection Admin access on every ADO org
8 | Source-side | PAT issued for migration service identity
9 | Source-side | Inventory of 100 repos with owner, BU, size, PR counts, integrations
10 | Source-side | Approval to install Azure Boards GitHub App at ADO org level
11 | Target-side | Target GHE orgs pre-created (1:1 with ADO orgs)
12 | Target-side | Baseline ruleset JSON template approved
13 | Tooling | GitHub CLI + gh-gei + gh-ado2gh installed on migration workstation
14 | Tooling | Azure Key Vault (or equivalent) for migration secrets
15 | Network | Outbound HTTPS to *.github.com permitted (proxy whitelist updated)
16 | Governance | Sponsor + steering committee + RAID log live
17 | Governance | Pilot wave volunteers confirmed (3-5 repos, low-risk)
18 | Pipelines | Azure Pipelines GitHub App install approved on GHE org(s)
Saudi MoJ | ADO -> GHE | Phase 1 Plan
5 / 18
Notes: Walk through each pre-requisite category. Highlight commercial (EMU contract must be signed before Week 1), identity (book MoJ Entra admin now), source-side (PCA on all ADO orgs), target-side (orgs pre-created, ruleset JSON approved), tooling (gh-gei + gh-ado2gh installed), network (proxy whitelist), governance (sponsor + steering), and pipelines (Azure Pipelines GitHub App approval). If any of these slips, the program slips 1:1.

## Slide 6
Duration & Timeline
10 calendar weeks across 5 stages with 5 milestones
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
S0 Mobilise & Discovery
S1 Identity & Foundation
S2 Pilot Wave (5 repos)
S3 Production Waves 1-4
S4 Stabilisation & Close
M1
M2
M3
M4
M5
Milestones
# | Milestone | Exit Gate | Week
M1 | Mobilise & Discovery done | Steering signs wave plan + risks | End W2
M2 | Identity Foundation live | EMU + SAML + SCIM in production | End W4
M3 | Pilot Wave done | 5 repos live, Boards linked, pipelines re-pointed | End W6
M4 | Production Waves done | 100 repos in GHE, pipelines green | End W9
M5 | Phase 1 closed | Hypercare exit, ADO archived, Phase 2 mandate | End W10
Saudi MoJ | ADO -> GHE | Phase 1 Plan
6 / 18
Notes: Walk through the Gantt. Five stages over 10 weeks. M2 is the critical gate -- identity foundation -- because everything downstream depends on EMU + SAML + SCIM being live. Waves 1-4 overlap in weeks 7-9, with a hard cap of two waves in flight at any time to protect hypercare capacity.

## Slide 7
Team & Resource Plan
8 people, ~5.3 peak FTE, ~150 person-days delivery effort
# | Role | Headcount | FTE | Weeks Active | Person-days
1 | Program Manager | 1 | 0.5 | 10 | 25
2 | Tech Lead / Architect | 1 | 1.0 | 10 | 50
3 | IAM Engineer | 1 | 0.5 (front-loaded) | 10 | 14
4 | Platform / Migration Engineer #1 | 1 | 1.0 | 8 (W3-W10) | 40
5 | Platform / Migration Engineer #2 | 1 | 1.0 | 8 (W3-W10) | 40
6 | DevEx Engineer (pipelines) | 1 | 0.7 | 6 (W5-W10) | 21
7 | InfoSec Engineer | 1 | 0.3 | 8 (W3-W10) | 12
8 | Change Manager / Comms | 1 | 0.3 | 10 | 15
 | TOTAL | 8 | 5.3 peak |  | 217 capacity / 150 effort
Capacity vs Effort
150 p-days = billable
value-added effort.
217 p-days = nominal team
capacity (8 ppl x weeks x FTE).
Gap = ~67 p-days of
realistic slack: meetings,
handovers, waiting on deps,
hypercare standby.
Implies ~65-70% utilisation,
which is normal for change-
heavy programs.
Available on-demand (NOT on delivery headcount)
- Sponsor (steering chair) - MoJ ADO Project Collection Admins - Repo Owners (~100, smoke-test sign-off)
- Application SMEs / process owners - Procurement / Licensing - IT Ops (CMDB updates at archive)
Saudi MoJ | ADO -> GHE | Phase 1 Plan
7 / 18
Notes: Eight people, 5.3 peak FTE. Note the gap between 217 capacity person-days and 150 effort person-days -- that's normal slack for change-heavy work. Tech Lead and the two Platform Engineers are the largest contributors. The IAM Engineer is the smallest contributor by p-days but the highest-risk single point of failure -- their availability in weeks 3-4 is non-negotiable. Roles outside the 8 (sponsor, ADO admins, repo owners) are on-demand consultees, not delivery headcount.

## Slide 8
Resource Heatmap
Effort intensity by role across the five stages
S0 Mobilise
S1 Foundation
S2 Pilot
S3 Waves
S4 Close
Program Manager
Normal
Normal
Normal
Normal
Normal
Tech Lead / Architect
Normal
Normal
Normal
Normal
Light
IAM Engineer
Light
Peak
Light
Light
Off
Platform Eng x2
Light
Normal
Peak
Peak
Light
DevEx Engineer
Off
Light
Peak
Peak
Light
InfoSec Engineer
Light
Light
Normal
Normal
Normal
Change Manager
Peak
Light
Normal
Normal
Light
Legend
Peak
Normal
Light
Off
Critical: IAM Engineer is the single biggest schedule risk. SAML + SCIM peak is Weeks 3-4. Book MoJ IAM resource at Week 1 and have a backup.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
8 / 18
Notes: Heatmap shows when each role is hot. IAM peaks in Stage 1. Platform Eng pair peak in Stages 2 and 3. DevEx peaks in Stages 2 and 3 (pipeline re-pointing). Change Manager peaks at Stage 0 (comms plan + templates) and then settles to normal. Bottom strip: book a backup IAM resource for weeks 3-4.

## Slide 9
Effort Breakdown by Workstream
150 person-days across 11 workstreams
# | Workstream | Effort (p-days) | % of Total
WS1 | Program Management & PMO | 25 | 17%
WS2 | Identity & Access (EMU + SAML + SCIM) | 14 | 9%
WS3 | Platform / Migration Factory | 10 | 7%
WS4 | Repo Migration (Pilot + 4 waves) | 25 | 17%
WS5 | Azure Boards GitHub App Integration | 4 | 3%
WS6 | Pipeline Source Re-pointing | 20 | 13%
WS7 | Security, Policy & Rulesets | 7 | 5%
WS8 | Comms & Training | 15 | 10%
WS9 | Decommission Prep (read-only freeze) | 5 | 3%
WS10 | Hypercare (x5 waves) | 15 | 10%
WS11 | Contingency (10%) | 10 | 7%
 | TOTAL | 150 | 100%
Top Effort Drivers
1. PMO + Repo Migration (25 p-days each)
Largest cost centres
2. Pipeline Re-pointing (20 p-days)
Higher if Classic-pipeline heavy
3. Comms & Training (15 p-days)
Underestimating this is the #1
reason large migrations slip
4. Hypercare (15 p-days)
Cap concurrent waves at 2
5. IAM (14 p-days)
Critical path -- highest schedule
risk despite lower effort
Saudi MoJ | ADO -> GHE | Phase 1 Plan
9 / 18
Notes: Workstream breakdown. PMO and Repo Migration are the two largest cost centres at 25 p-days each. Pipeline re-pointing is 20 p-days and is the line item most likely to slip if the Classic-pipeline ratio is high. Comms and Training (15 p-days) is consistently underestimated in this kind of program -- be ruthless about not cutting it.

## Slide 10
L1 Plan - Milestones
Five sequential stages with explicit exit gates
# | Milestone | Exit Gate | Calendar Week
M1 | Mobilise & Discovery complete | Steering sign-off on scope, wave plan, risk register | End of Week 2
M2 | Identity Foundation live | EMU + SAML + SCIM in production, >=95% users provisionable | End of Week 4
M3 | Pilot Wave complete | 5 repos migrated, Boards link verified, pipelines re-pointed, retrospective signed off | End of Week 6
M4 | Production Waves complete | All 100 repos in GHE, all in-scope pipelines re-pointed and green | End of Week 9
M5 | Phase 1 closed | Hypercare exited, ADO repos archived, lessons logged, Phase 2 mandate decision taken | End of Week 10
Critical Path
Sponsor sign-off
Discovery & inventory
Identity foundation
Factory smoke test
Pilot wave
M3 gate
Waves 1-4 (overlap)
M5 close
Critical Path Risk
The identity foundation (M2) is the longest-pole dependency.
Any delay in MoJ Entra ID admin availability for SAML / SCIM will slip the whole program 1:1.
Mitigation: book MoJ IAM resource in Week 1 and front-load the SCIM dry-run.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
10 / 18
Notes: L1 milestones. Five gates, each with explicit exit criteria. The critical path runs through M2 (identity foundation). If M2 slips, everything slips. The mitigation -- book MoJ IAM resource at kickoff -- is on the next slide as Decision D8.

## Slide 11
L2 Plan - Workstream Activities
Stages 0 & 1: Mobilise, Discovery, Identity, Foundation
Stage 0 - Mobilise & Discovery (W1-2, ~20 p-days)
Activity | Owner | Days
Charter, RACI, steering setup | PM | 2
RAID log & first review | PM | 1
Comms plan, templates, distribution lists | Change | 3
Identity mapping CSV (ADO -> Entra UPN) | IAM | 3
Inventory all 100 repos | Platform | 3
Inventory all pipelines per repo | DevEx | 2
Inventory ADO branch policies per repo | Platform | 2
Baseline ruleset JSON definition | InfoSec | 2
Wave assignment (Pilot + 4 waves) | Tech Lead | 2
Stage 1 - Identity & Foundation (W3-4, ~22 p-days)
Activity | Owner | Days
EMU enterprise shell configuration | IAM | 2
SAML SSO with MoJ Entra ID | IAM | 3
SCIM provisioning Entra -> GHE | IAM | 3
Identity UAT with 10 test users | IAM+TL | 2
Migration factory: parameterised GEI scripts | Platform | 3
Secret vaulting (PATs in Key Vault) | Platform | 1
Migration tracking dashboard | Platform | 2
Sandbox GHE org for dry-runs | Platform | 1
Ruleset application script | InfoSec | 1
Comms templates finalised | Change | 2
Stage Exit Gates
M1 (W2): Steering signs off scope, wave plan, and risk register.
M2 (W4): EMU + SAML + SCIM in production. End-to-end factory smoke test passes against a throwaway repo.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
11 / 18
Notes: L2 breakdown for Stages 0 and 1. Stage 0 is parallel discovery streams (repos, pipelines, policies, identity). Stage 1 is identity foundation and migration factory build. The end-to-end factory smoke test against a throwaway repo is the gate that authorises the pilot.

## Slide 12
L2 Plan - Pilot Wave (Stage 2)
Weeks 5-6: 5 low-risk repos, end-to-end validation
Activity | Owner | Days
Pilot wave kickoff & comms | PM + Change | 1
Dry-run pilot migration in sandbox | Migration Pod | 1
Pilot Go/No-Go meeting | Steering | 0.5
Freeze pilot ADO repos (read-only) | ADO Admin | 0.5
Execute pilot migration (5 repos) | Migration Pod | 1
Apply rulesets + CODEOWNERS to pilot repos | InfoSec + Platform | 1
Install Azure Boards GitHub App on GHE pilot org | Platform + ADO Admin | 0.5
Connect Boards App to ADO org/projects | Platform + ADO Admin | 0.5
Test AB#123 linking (commits, PRs, branches, merge) | DevEx + Owners | 1
Install Azure Pipelines GitHub App on GHE org | Platform | 0.5
Re-point pilot pipelines (5-10 pipelines) | DevEx | 2
Validate build + release end-to-end | DevEx + Owners | 1
Mannequin reclamation for pilot | Platform | 1
Hypercare D+1 -> D+3 | Wave Lead + Pods | 2
Archive pilot ADO repos (D+7) | ADO Admin | 0.5
Pilot retrospective + runsheet update | PM | 1
M3 gate: pilot accepted, scale authorised | Steering | 0.5
Pilot exits cleanly when: 5 repos live, Boards links verified, pipelines green, zero P1/P2 defects open, retrospective signed off.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
12 / 18
Notes: L2 for the pilot wave. 17 activities. Two-thirds of the value of the pilot is in step 13 (smoke tests + sign-off by repo owners) and step 14 (3 days of hypercare). Do not skip them. The pilot retrospective at step 16 feeds runsheet updates that all four production waves consume.

## Slide 13
L2 Plan - Production Waves (Stage 3)
Weeks 7-9: 4 waves of ~25 repos each, 2 in flight at a time
Per-Wave Template (~11 p-days, repeated 4x)
# | Activity | Owner | Days
1 | Wave manifest confirmed (repos, owners, pipelines) | Wave Lead | 0.5
2 | T-10 / T-3 / T-1 comms | Change Mgr | 1
3 | Dry-run wave migration in sandbox | Migration Pod | 1
4 | Go / No-Go meeting | Steering | 0.5
5 | Freeze wave ADO repos | ADO Admin | 0.5
6 | Execute migration (25 repos in parallel) | Migration Pod | 1
7 | Apply rulesets + CODEOWNERS | InfoSec + Platform | 0.5
8 | Verify Boards integration on new repos | DevEx | 0.5
9 | Re-point pipelines for wave (~25-50 pipelines) | DevEx | 3
10 | Validate builds for wave | DevEx + Owners | 1
11 | Mannequin reclamation | Platform | 1
12 | Hypercare D+1 -> D+3 | Wave Lead + Pods | 2
13 | Archive wave ADO repos (D+7) | ADO Admin | 0.5
Wave Cadence
W7 W8 W9
[--W1--]
[--W2--]
[--W3--]
[--W4--]
Max 2 waves in flight.
No new wave starts
during another wave's
D-0 -> D+3 window.
4 x 25 = 100 repos
all live by end W9.
Total Stage 3 effort: ~44 p-days | Calendar duration: 3 weeks | M4 gate: 100 repos in GHE, pipelines green
Saudi MoJ | ADO -> GHE | Phase 1 Plan
13 / 18
Notes: L2 for production waves. Per-wave template is ~11 p-days, repeated four times. Two waves overlap in flight. Total Stage 3 effort is ~44 p-days in a 3-week calendar window. The strict 'no new wave during another wave's D-0 to D+3' rule is what stops hypercare from collapsing.

## Slide 14
L3 Plan - Detailed Task Sample
Stage 0 task breakdown (full L3 covers ~80 numbered tasks)
ID | Task | Owner | Days | Predecessors
0.1 | Sponsor sign-off & charter | PM | 1 | -
0.2 | RACI agreed | PM | 0.5 | 0.1
0.3 | Steering committee chartered, first meeting | PM | 0.5 | 0.1
0.4 | RAID log v1 published | PM | 1 | 0.1
0.5 | Comms plan signed off | Change Mgr | 2 | 0.1
0.6 | Stakeholder & contact matrix (per repo) | Change Mgr | 1 | 0.1
0.7 | Pull ADO users from all 100 repos | IAM | 1 | 0.1
0.8 | Identity mapping CSV (ADO/Entra/EMU) | IAM | 2 | 0.7
0.9 | Inventory: gh ado2gh inventory-report | Platform | 1 | 0.1
0.10 | Repo size + LFS audit | Platform | 1 | 0.9
0.11 | Open PRs + open branches snapshot | Platform | 1 | 0.9
0.12 | Pipeline inventory per repo (YAML vs Classic) | DevEx | 2 | 0.9
0.13 | ADO branch policy inventory per repo | Platform | 2 | 0.9
0.14 | ADO service connections inventory | DevEx | 1 | 0.9
0.15 | Complexity scoring per repo | Tech Lead | 1 | 0.10-0.14
0.16 | Wave assignment (Pilot + W1-W4) | Tech Lead | 1 | 0.15
0.17 | Baseline ruleset JSON v1 | InfoSec | 2 | 0.13
0.18 | CODEOWNERS template | Platform | 0.5 | -
0.19 | M1 gate: sign-off on wave plan & risks | PM + Sponsor | 0.5 | 0.16, 0.17
Full L3 covers ~80 tasks across all 5 stages. Available as CSV / project plan on request.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
14 / 18
Notes: Illustrative L3 cut for Stage 0 -- 19 tasks. The full L3 is ~80 tasks across all five stages. Each task has owner, effort, and predecessor. The CSV export of the full L3 is available alongside this deck for import into project tooling.

## Slide 15
Phase 1 Risks & Mitigations
Top 10 risks ranked
# | Risk | L | I | Mitigation
R1 | Entra SAML / SCIM delayed (MoJ admin availability) | Med | High | Book MoJ IAM in W1; backup admin
R2 | Pipeline re-point harder than expected (Classic %) | Med | High | Inventory Classic % early; +20% buffer
R3 | Branch policies don't map perfectly to rulesets | Low | Med | Baseline ruleset + per-repo exceptions list
R4 | Mannequin reclamation gaps (ex-staff) | High | Low | Define unreclaimed-mannequin policy
R5 | LFS / oversize repos exceed GHE limits | Low | High | Audit in Stage 0; remediate before wave assignment
R6 | Hardcoded ADO URLs in IaC / pipelines / docs | Med | Med | Inventory in Stage 0; redirect map; comms
R7 | Boards App rate limits across 100 repos | Low | Med | Stagger app install; monitor
R8 | Concurrent waves overload hypercare team | Med | Med | Hard cap 2 waves concurrent
R9 | Repo owners not available for smoke tests | Med | Med | Confirm at T-10; escalation path
R10 | Pipeline secrets recreation gaps | Med | High | Secret inventory per pipeline; checklist
Saudi MoJ | ADO -> GHE | Phase 1 Plan
15 / 18
Notes: Top 10 risks. R1 (IAM availability) and R2 (Classic pipelines) are the schedule risks. R5 (LFS / oversize repos) is the data-integrity risk -- audit early. R8 (concurrent waves overloading hypercare) is the operational risk that the wave cadence rule mitigates. R10 (pipeline secrets) is the silent risk -- builds will look fine until they try to deploy.

## Slide 16
Decisions Required at Mobilise
Steering must close these in Week 1
# | Decision | Recommendation | Owner
D1 | Pilot wave repos (5) | Low-risk, willing teams, mix of YAML + Classic pipelines | Steering
D2 | GHAS in scope for Phase 1? | YES - code scanning + secret scanning + Dependabot baseline | InfoSec + Sponsor
D3 | Disable GitHub Issues per repo? | YES - Boards stays in ADO; avoid drift | Steering
D4 | Mannequin policy for ex-staff | Leave unreclaimed after 30 days; attribute to bot account | InfoSec + IAM
D5 | Auto-state-transition rules per work item type | Use ADO defaults; document per project | Apps SMEs
D6 | ADO retention window post-archive | 90 days read-only, then delete | Sponsor + InfoSec
D7 | Concurrent wave cap | 2 waves max in flight | Steering
D8 | Backup IAM resource for SAML / SCIM peak | Identify named backup before Week 3 | Sponsor
D9 | Hypercare on-call rota across waves | Dedicated rota; no double-booking with delivery work | PM
D10 | Branch protection enforcement on day one? | YES - block non-compliant pushes from cutover | InfoSec
Saudi MoJ | ADO -> GHE | Phase 1 Plan
16 / 18
Notes: Ten decisions for steering to close in week 1. D2 (GHAS in or out) drives security baseline. D3 (disable Issues) prevents work-item drift. D4 (mannequin policy) sets expectations for ex-staff. D7 (concurrent waves cap) protects hypercare. D8 (backup IAM) is the single most important risk mitigation.

## Slide 17
Phase 2 Preview (Not in this estimate)
Migrate CI/CD to GitHub Actions after Phase 1 close
Phase 2 Scope
- Convert Azure Pipelines -> GitHub Actions
workflows (use gh actions-importer)
- Re-platform Release pipelines to GitHub
Actions Environments + approvals + gates
- Stand up self-hosted runners on Azure VMSS
- OIDC federation to Azure subscriptions
(eliminate service-connection secrets)
- Decommission Azure Pipelines / Releases
Indicative Effort
Theme | Effort
Actions Importer setup & audit | 5 p-days
Self-hosted runners (VMSS) | 8 p-days
OIDC federation to Azure | 3 p-days
Pipeline conversion (avg per pipeline) | 0.5-2 p-days
Release pipeline conversion (per release) | 1-3 p-days
Hypercare + cutover per wave | 3 p-days
Indicative Phase 2 duration: 12-16 weeks | Effort: 200-250 person-days
Note
A detailed Phase 2 estimate should be produced at Phase 1 close (M5)
when actual pipeline counts, Classic vs YAML ratio, and per-environment release complexity are known.
Phase 2 is dependent on a successful Phase 1 hypercare exit -- it is not initiated in parallel.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
17 / 18
Notes: Phase 2 is intentionally out of scope. CI/CD migration to GitHub Actions, runners on VMSS, OIDC to Azure, and Azure Pipelines decommission. Indicative 12-16 weeks and 200-250 p-days. The detailed Phase 2 estimate must be produced at M5 close, not now -- we won't know actual pipeline counts and complexity until we have walked through them in Phase 1.

## Slide 18
Next Steps
Decisions and actions to authorise Week 1
1
Confirm Phase 1 scope and approach
Steering signs off this deck. Locks the hybrid model: code in GHE, work items + releases in ADO.
2
Close the 10 mobilise decisions (D1-D10)
Especially: pilot 5 repos, GHAS in/out, mannequin policy, backup IAM resource.
3
Confirm GHE Enterprise (EMU) procurement and tenant
Procurement and licensing in place before Week 1.
4
Confirm team composition (8 roles)
Named individuals across PM, Tech Lead, IAM, 2x Platform, DevEx, InfoSec, Change.
5
Book MoJ Entra ID admin for SAML + SCIM in Weeks 3-4
Highest-risk dependency. Must be booked at kick-off, not later.
6
Issue ADO PAT for migration service identity and vault it
Required by Platform team in Week 2 for inventory + dry-runs.
7
Kick off Stage 0 - Mobilise & Discovery
Week 1 starts. Inventory of 100 repos begins. M1 gate at end of Week 2.
Saudi MoJ | ADO -> GHE | Phase 1 Plan
18 / 18
Notes: Seven next steps to authorise Week 1. The two that have lead time are step 3 (EMU procurement) and step 5 (booking MoJ Entra admin). Both must start now, before steering signs off scope, or they will become the schedule bottleneck.